## Project Plan and Gantt
PROJECT PLAN AND GANTT CHART TEMPLATE
PROJECT NAME | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
Product Release | 2022-09-02 | 2022-10-10 |  | 20%
SCOPE STATEMENT
TASKS | START | END | DAYS | STATUS
Data collection though internet | 2022-05-01 | 2022-05-15 | 14 | Complete
Introduction | 2022-05-20 | 2022-05-29 | 9 | In Progress
Literature review | 2022-06-01 | 2022-06-10 | 9 | In Progress
Research methodology | 2022-06-11 | 2022-06-15 | 4 | In Progress
Development of questionnaire | 2022-06-16 | 2022-06-20 | 4 | In Progress
Distrubution of Questionnaire | 2022-06-21 | 2022-06-25 | 4 | In Progress
Collection of Data | 2022-06-17 | 2022-06-25 | 8 | Not Started
Analysis of Data | 2022-06-26 | 2022-06-30 | 4 | Not Started
Analysis of Data at SPSS software | 2022-07-01 | 2022-07-09 | 8 | Not Started
Discussion of data | 2022-07-10 | 2022-07-15 | 5 | Not Started
Conclusion | 2022-07-16 | 2022-07-20 | 4 | Not Started
Review of whole dissertation | 2022-07-21 | 2022-07-25 | 4 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Project Plan and Gantt - BLANK
PROJECT PLAN AND GANTT CHART
PROJECT NAME | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
DESIGNING A CHABOT FOR BETTER CUSTOMER SERVICES | 15/6/2022 | 2022-09-15
SCOPE STATEMENT
TASKS | START | END | DAYS | STATUS
Data collection Internet Sources | 2022-05-15 | 2022-05-20 | 5 | Complete
Introduction | 2022-06-01 | 2022-06-15 | 14 | Complete
Literature Review | 2022-06-16 | 2022-06-25 | 9 | Complete
Research Methodology | 2022-06-27 | 2022-06-29 | 2 | Complete
Python ERP Flask Application | 2022-06-30 | 2022-07-02 | 2 | Complete
Programming Phase Tool | 2022-07-03 | 2022-07-10 | 7 | Complete
Analysis of Tool | 2022-07-05 | 2022-07-11 | 6 | Complete
Analysis of Data at Python software | 2022-07-10 | 2022-07-13 | 3 | Complete
Discussion of data | 2022-07-13 | 2022-07-15 | 2 | Complete
Conclusion | 2022-07-15 | 2022-07-15 | 0 | Complete
Review of whole dissertation | 2022-09-06 | 2022-09-09 | 3 | Not Started
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Stakeholder List
STAKEHOLDER LIST
NAME | POSITION | ROLE IN PROJECT | EMAIL ADDRESS | REQUIREMENTS | EXPECTATIONS
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
COST BASELINE
ITEM / TASK | % COMPLETE | BASE COST | COST | ACTUAL COST | % BUDGET SPENT
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
COMMUNICATION PLAN
COMMUNICATION TYPE | DELIVERABLE | DESCRIPTION | DELIVERY METHOD | FREQUENCY | OWNER | AUDIENCE
Presentation | 15-minute PowerPoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.